## Planned Induction
Master Work Schedule Log (UNCLASSIFIED)
(Mon Mar 18 09:02:23 EDT 2024)
for Workload Year 2024
for SAC 2
for Status 3
MWSLIN | SOR | NSN | TAMCN | NOMENCLATURE | Prior | Current | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
[5 empty] | 502 | 798 | 40 | 37 | 21 | 57 | 16 | 64 | 63 | 102 | 79 | 77 | 76 | 66 | 25 | 25 | 25 | 25
C768 | PPA | 1240015541735 | E0846 | Thermal Elbow Assembly TSS | 84 | 12 |  |  |  | 12
D009 | PPB | 5895015525616 | A0123 | Console, Communications | 8 | 15 | 12 | 3
D046 | PPA | 5820200058054 | A0153 | Receiver-Transmitter, Radio | 192 | 0
D052 | PPA | 5998011423769 | A2179 | Electronic Component | 12 | 0
D081 | PPA | 6625014778172 | A7420 | Generator, Function, Electronic :33250A | 6 | 0
D084 | PPA | 6625015623698 | A7420 | Calibrator, Range Indicator | 11 | 0
D090 | PPA | 6625016533190 | A7523 | Calibrator, Frequency | 2 | 0
D091 | PPB | 6130015447811 | A2179 | Power Supply, ComTech |  | 2 | 2
D092 | PPA | 6625015658920 | A7420 | Oscilloscope | 1 | 0
D095 | PPA | 5998011418146 | A2179 | Circuit Card Assembly | 1 | 0
D097 | PPA | 5996015848748 | A0331 | Amplifier, Radio | 20 | 20 | 10 | 10
D098 | PPA | 5996016616649 | A0242 | Amplifier, Radio Frequency | 6 | 3 |  |  |  |  | 3
D0A2 | PPA | 6625014217497 | A7596 | Plug-In Unit, Electr | 1 | 0
D0A3 | PPA | 6625014925646 | A7596 | Plug-In Unit, Electrical-Electronic |  | 1 |  | 1
D752 | PPA | 6660015066613 | E1035 | Theodolite, Meteorological | 3 | 1 | 0 | 1
D755 | PPA | 1290015100540 | E0180 | Transit, Aming Circle | 35 | 25 | 5 | 5 | 8 | 7
D755 | PPB | 1290015100540 | E0180 | Transit, Aming Circle | 25 | 19 | 6 | 6 | 7
D769 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly | 4 | 1 | 1
D776 | PPA | 1440014583366 | E0942 | Armament, Control | 2 | 0
D785 | PPA | 4910015991753 | E7903 | Test Adapter Vehicle | 2 | 1 |  | 1 |  | 0
D798 | PPA | 2815015502615 | E0947 | Engine, Diesel | 9 | 0
D798 | PPB | 2815015502615 | E0947 | Engine, Diesel | 7 | 0
D7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section | 5 | 3 | 3
D815 | PPA | 5980016296933 | B1583 | Control-Display, Opt
D826 | PPB | 2815015891633 | B0071 | Engine, Diesel | 1 | 0
D842 | PPA | 4520016313780 | B0055 | Heater, Water, Liquid | 1 | 0
D930 | PPB | 1240015158265 | E0671 | Mount, Telescope | 13 | 0
E032 | PPB | 5820015709746 | A0097 | Vehicular, Adaptor Unit |  | 300 |  |  |  | 25 |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
E097 | PPA | 5996015848748 | A0331 | Amplifier, Radio |  | 50 |  |  |  | 10 | 10 | 10 | 10 | 10
E0A4 | PPA | 6625014925557 | A7596 | Plug-In Unit, Electronic Test Equip |  | 3 |  |  | 3 | 0
E0A5 | PPA | 5996016429980 | A0352 | Amplifier, Radio frequency |  | 1 |  |  |  | 1
E0A6 | PPA | 6625014925302 | A7596 | Plug-In Unit, Electric |  | 6 | [7 empty] | 3 |  |  | 3
E70S | PPA | 2815015502608 | E0947 | Engine, Diesel |  | 20 | [5 empty] | 2 | 5 | 5 | 4 | 4
E766 | PPB | 1025992979085 | E0671 | Buffer, Assembly, Special |  | 7 | [8 empty] | 2 | 2 | 2 | 1
E771 | PPB | 3040994887463 | E0671 | Accumulator, Hydraulic |  | 2 |  |  |  |  | 1 | 1
E772 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 8 | [5 empty] | 2 | 2 | 2 | 2
E776 | PPA | 1440014583366 | E0942 | Armament, Control |  | 4 | [7 empty] | 4
E7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 6 | [5 empty] | 4 | 2
E930 | PPB | 1240015158265 | E0671 | Mount, Telescope |  | 12 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2
L461 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly |  | 22 | [5 empty] | 2 | 4 | 4 | 4 | 4 | 4
L463 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 15 | [5 empty] | 5 | 5 | 5
L464 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 13 | [5 empty] | 6 | 7
L465 | PPB | 5895016647511 | E0671 | Enclosure Assembly, Radio |  | 3 | [5 empty] | 3
M80C | DMISA | 2805015556505 | C4548 | Engine, Outboard Multi Fuel | 50 | 0
R2AA | DMISA | 5985015821343 | A0169 | Antenna |  | 200 | [7 empty] | 40 | 40 | 40 | 40 | 40
R379 | PPA | 6675002932930 |  | Clinometers |  | 8 | 0 | 2 |  | 2 |  | 2 |  | 2
R380 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 2 |  |  | 1 |  | 1
R397 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 4 | 1 | 0 | 1 |  | 1 |  | 1
R3A7 | PPA | 4920001616963 |  | Boresight Equipment | 1 | 1 |  |  | 1 |  | 0
R479 | PPA | 6675002932930 |  | Clinometers |  | 1 |  | 1
R480 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 1 |  | 1
R497 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 1 |  | 1
V413 | PPA | 6625014962745 |  | Multiproduct Calibrator |  | 1 |  | 1
W375 | PPA | 8120015271059 |  | Cylinder, Compressed Gas |  | 4 |  | 4

## Planned Production
Master Work Schedule Log (UNCLASSIFIED)
(Mon Mar 18 09:02:23 EDT 2024)
for Workload Year 2024
for SAC 2
for Status 3
MWSLIN | SOR | NSN | TAMCN | NOMENCLATURE | Prior | Current | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
[5 empty] | 373 | 927 | 36 | 31 | 58 | 31 | 16 | 60 | 21 | 105 | 67 | 137 | 93 | 42 | 86 | 44 | 25 | 25 | 25 | 25
C768 | PPA | 1240015541735 | E0846 | Thermal Elbow Assembly TSS | 84 | 12 | [5 empty] | 12
D009 | PPB | 5895015525616 | A0123 | Console, Communications |  | 23 | 0 | 8 | 12 | 3
D046 | PPA | 5820200058054 | A0153 | Receiver-Transmitter, Radio | 166 | 26 | 0 | 0 | 26
D052 | PPA | 5998011423769 | A2179 | Electronic Component | 8 | 4 | 4
D081 | PPA | 6625014778172 | A7420 | Generator, Function, Electronic :33250A | 3 | 3 | 3
D084 | PPA | 6625015623698 | A7420 | Calibrator, Range Indicator | 7 | 4 | 0 | 4
D090 | PPA | 6625016533190 | A7523 | Calibrator, Frequency | 1 | 1 | 0 |  | 1
D091 | PPB | 6130015447811 | A2179 | Power Supply, ComTech |  | 2 |  | 2 |  | 0
D092 | PPA | 6625015658920 | A7420 | Oscilloscope |  | 1 |  | 1 | 0
D095 | PPA | 5998011418146 | A2179 | Circuit Card Assembly | 1 | 0
D097 | PPA | 5996015848748 | A0331 | Amplifier, Radio |  | 40 |  |  |  |  | 0 | 10 | 10 | 10 | 10
D098 | PPA | 5996016616649 | A0242 | Amplifier, Radio Frequency |  | 9 | [6 empty] | 3 | 3 | 3
D0A2 | PPA | 6625014217497 | A7596 | Plug-In Unit, Electr |  | 1 | 0 | 1
D0A3 | PPA | 6625014925646 | A7596 | Plug-In Unit, Electrical-Electronic |  | 1 |  | 1
D752 | PPA | 6660015066613 | E1035 | Theodolite, Meteorological | 1 | 3 | 0 | 0 | 2 |  | 1
D755 | PPA | 1290015100540 | E0180 | Transit, Aming Circle | 15 | 45 | 7 | 3 | 5 | 12 | 9 | 9
D755 | PPB | 1290015100540 | E0180 | Transit, Aming Circle | 17 | 27 | 8 | 6 | 6 | 7 | 0
D769 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly |  | 5 | 4 |  |  | 1 | 0
D776 | PPA | 1440014583366 | E0942 | Armament, Control |  | 2 | 2
D785 | PPA | 4910015991753 | E7903 | Test Adapter Vehicle |  | 3 | 2 |  |  |  | 1
D798 | PPA | 2815015502615 | E0947 | Engine, Diesel |  | 9 |  | 3 | 3 | 3 | 0
D798 | PPB | 2815015502615 | E0947 | Engine, Diesel | 6 | 1 | 1
D7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section | 5 | 3 |  |  | 3
D815 | PPA | 5980016296933 | B1583 | Control-Display, Opt
D826 | PPB | 2815015891633 | B0071 | Engine, Diesel |  | 1 | 1 |  |  |  | 0
D842 | PPA | 4520016313780 | B0055 | Heater, Water, Liquid |  | 1 |  | 1
D930 | PPB | 1240015158265 | E0671 | Mount, Telescope | 9 | 4 | 3 | 1
E032 | PPB | 5820015709746 | A0097 | Vehicular, Adaptor Unit |  | 300 |  |  |  |  | 0 | 25 |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
E097 | PPA | 5996015848748 | A0331 | Amplifier, Radio |  | 50 | [9 empty] | 10 | 10 | 10 | 10 | 10
E0A4 | PPA | 6625014925557 | A7596 | Plug-In Unit, Electronic Test Equip |  | 3 |  |  |  | 0 | 3
E0A5 | PPA | 5996016429980 | A0352 | Amplifier, Radio frequency |  | 1 | [5 empty] | 1
E0A6 | PPA | 6625014925302 | A7596 | Plug-In Unit, Electric |  | 6 | [9 empty] | 3 |  |  | 3
E70S | PPA | 2815015502608 | E0947 | Engine, Diesel |  | 20 | [6 empty] | 5 | 4 | 5 | 5 | 1
E766 | PPB | 1025992979085 | E0671 | Buffer, Assembly, Special |  | 7 | [10 empty] | 2 | 2 | 2 | 1
E771 | PPB | 3040994887463 | E0671 | Accumulator, Hydraulic |  | 2 | [6 empty] | 1 | 1
E772 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 8 | [7 empty] | 2 | 2 | 2 | 2
E776 | PPA | 1440014583366 | E0942 | Armament, Control |  | 4 | [10 empty] | 4
E7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 6 | [7 empty] | 5 | 1
E930 | PPB | 1240015158265 | E0671 | Mount, Telescope |  | 12 | [7 empty] | 2 | 2 | 2 | 2 | 2 | 2
L461 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly |  | 22 | [8 empty] | 2 | 4 | 5 | 3 | 4 | 4
L463 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 15 | [7 empty] | 5 | 5 | 5
L464 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 13 | [7 empty] | 6 | 7
L465 | PPB | 5895016647511 | E0671 | Enclosure Assembly, Radio |  | 3 | [8 empty] | 3
M80C | DMISA | 2805015556505 | C4548 | Engine, Outboard Multi Fuel | 50 | 0
R2AA | DMISA | 5985015821343 | A0169 | Antenna |  | 200 | [7 empty] | 40 |  | 80 | 40 |  | 40
R379 | PPA | 6675002932930 |  | Clinometers |  | 8 |  |  | 0 |  | 2 |  | 2 |  | 2 |  | 2
R380 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 2 |  |  |  | 0 |  | 1 |  | 1
R397 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 4 |  |  | 0 | 1 |  | 1 |  | 1 |  | 1
R3A7 | PPA | 4920001616963 |  | Boresight Equipment |  | 2 | 1 | 0 |  |  |  | 1
R479 | PPA | 6675002932930 |  | Clinometers |  | 1 | [13 empty] | 1
R480 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 1 | [13 empty] | 1
R497 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 1 | [13 empty] | 1
V413 | PPA | 6625014962745 |  | Multiproduct Calibrator |  | 1 | [13 empty] | 1
W375 | PPA | 8120015271059 |  | Cylinder, Compressed Gas |  | 4 |  |  |  | 4

## DLH PhasingSchedule
Master Work Schedule Log (UNCLASSIFIED)
(Mon Mar 18 09:02:23 EDT 2024)
for Workload Year 2024
for SAC 2
for Status 3
MWSLIN | SOR | NSN | TAMCN | NOMENCLATURE | Prior | Current | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
[6 empty] | 27951.36 | 2323.27 | 1647.48 | 1454.51 | 1335.89 | 1260.42 | 1653.79 | 2298.99 | 2835.58 | 2550.67 | 2308.94 | 1930.27 | 1724.21 | 1292.29 | 928.81 | 860.41 | 860.43 | 495.84 | 189.56
C768 | PPA | 1240015541735 | E0846 | Thermal Elbow Assembly TSS |  | 84.88 |  |  |  | 32.54 | 41.03 | 11.31
D009 | PPB | 5895015525616 | A0123 | Console, Communications |  | 962.96 | 290.72 | 422.69 | 222.31 | 27.24
D046 | PPA | 5820200058054 | A0153 | Receiver-Transmitter, Radio |  | 127.65 | 51 | 49.36 | 27.29
D052 | PPA | 5998011423769 | A2179 | Electronic Component |  | 89.73 | 89.73
D081 | PPA | 6625014778172 | A7420 | Generator, Function, Electronic :33250A |  | 22.43 | 22.43
D084 | PPA | 6625015623698 | A7420 | Calibrator, Range Indicator |  | 10.79 | 7.86 | 2.93
D090 | PPA | 6625016533190 | A7523 | Calibrator, Frequency |  | 25.48 | 9.73 | 9.44 | 6.31
D091 | PPB | 6130015447811 | A2179 | Power Supply, ComTech |  | 60 | 18 | 42
D092 | PPA | 6625015658920 | A7420 | Oscilloscope |  | 8.29 | 4.58 | 3.71
D095 | PPA | 5998011418146 | A2179 | Circuit Card Assembly
D097 | PPA | 5996015848748 | A0331 | Amplifier, Radio |  | 1140 | 74.07 | 123.66 | 166.19 | 166.19 | 155.14 | 164.58 | 139.83 | 104.04 | 46.3
D098 | PPA | 5996016616649 | A0242 | Amplifier, Radio Frequency |  | 459 | 33.51 | 32.35 | 33.51 | 33.51 | 32.97 | 86.88 | 83.96 | 73.97 | 48.34
D0A2 | PPA | 6625014217497 | A7596 | Plug-In Unit, Electr |  | 34 | 30.15 | 3.85
D0A3 | PPA | 6625014925646 | A7596 | Plug-In Unit, Electrical-Electronic |  | 39 |  | 39
D752 | PPA | 6660015066613 | E1035 | Theodolite, Meteorological |  | 8.27 | 1.69 | 2.29 | 2.51 | 1.28 | 0.5
D755 | PPA | 1290015100540 | E0180 | Transit, Aming Circle |  | 1269.98 | 197.15 | 178.61 | 258.39 | 298.65 | 241.72 | 95.46
D755 | PPB | 1290015100540 | E0180 | Transit, Aming Circle |  | 1006.55 | 270.96 | 282.53 | 300.91 | 152.15
D769 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly |  | 242.7 | 115.55 | 51.51 | 53.21 | 22.43
D776 | PPA | 1440014583366 | E0942 | Armament, Control |  | 151 | 151
D785 | PPA | 4910015991753 | E7903 | Test Adapter Vehicle |  | 40.5 | 23.39 | 2.82 | 4.86 | 4.86 | 4.57
D798 | PPA | 2815015502615 | E0947 | Engine, Diesel |  | 646.66 | 292.75 | 213.64 | 106.62 | 33.65
D798 | PPB | 2815015502615 | E0947 | Engine, Diesel |  | 0 | 0
D7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 137.1 | 50.31 | 68.55 | 18.24
D815 | PPA | 5980016296933 | B1583 | Control-Display, Opt
D826 | PPB | 2815015891633 | B0071 | Engine, Diesel |  | 153.97 | 153.97
D842 | PPA | 4520016313780 | B0055 | Heater, Water, Liquid |  | 56.72 | 51.72 | 5
D930 | PPB | 1240015158265 | E0671 | Mount, Telescope |  | 329.44 | 314.35 | 15.09
E032 | PPB | 5820015709746 | A0097 | Vehicular, Adaptor Unit |  | 10500 |  |  |  | 247.91 | 422.91 | 612.53 | 772.91 | 758.34 | 831.24 | 962.51 | 860.41 | 831.24 | 962.54 | 831.22 | 860.41 | 860.43 | 495.84 | 189.56
E097 | PPA | 5996015848748 | A0331 | Amplifier, Radio |  | 1400 |  |  |  | 30.18 | 64.91 | 112.09 | 153.24 | 197.52 | 207.33 | 214.18 | 170.27 | 124.31 | 85.57 | 40.4
E0A4 | PPA | 6625014925557 | A7596 | Plug-In Unit, Electronic Test Equip |  | 32.1 |  |  | 11.22 | 16.59 | 4.29
E0A5 | PPA | 5996016429980 | A0352 | Amplifier, Radio frequency |  | 43.5 |  |  |  | 7.26 | 21.01 | 15.23
E0A6 | PPA | 6625014925302 | A7596 | Plug-In Unit, Electric |  | 624 | [7 empty] | 135.09 | 156 | 20.91 | 140.4 | 156 | 15.6
E70S | PPA | 2815015502608 | E0947 | Engine, Diesel |  | 730 | [5 empty] | 46.25 | 158.15 | 175.2 | 182.5 | 153.3 | 14.6
E766 | PPB | 1025992979085 | E0671 | Buffer, Assembly, Special |  | 301 | [8 empty] | 29.37 | 68.84 | 85.31 | 75.94 | 36.55 | 4.99
E771 | PPB | 3040994887463 | E0671 | Accumulator, Hydraulic |  | 30 |  |  |  |  | 2.75 | 13.01 | 11.99 | 2.25
E772 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 280 | [5 empty] | 24.51 | 53.66 | 68.85 | 74.65 | 49.04 | 9.29
E776 | PPA | 1440014583366 | E0942 | Armament, Control |  | 346 | [7 empty] | 100 | 115.2 | 119.04 | 11.76
E7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 294 | [5 empty] | 57.18 | 141.27 | 90.65 | 4.9
E930 | PPB | 1240015158265 | E0671 | Mount, Telescope |  | 492 | [5 empty] | 19.15 | 62.85 | 90.2 | 87.45 | 80.7 | 80.65 | 57.35 | 13.65
L461 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly |  | 1078 | [5 empty] | 11.46 | 59.88 | 134.92 | 188.86 | 200.32 | 200.36 | 153.52 | 101.32 | 27.36
L463 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 525 | [5 empty] | 40.8 | 134.25 | 192.7 | 125.25 | 32
L464 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 637 | [5 empty] | 102.9 | 278.39 | 221.41 | 34.3
L465 | PPB | 5895016647511 | E0671 | Enclosure Assembly, Radio |  | 126 | [5 empty] | 29.37 | 41.97 | 43.35 | 11.31
M80C | DMISA | 2805015556505 | C4548 | Engine, Outboard Multi Fuel
R2AA | DMISA | 5985015821343 | A0169 | Antenna |  | 1344 | [7 empty] | 268.8 | 250.8 | 286.8 | 268.8 | 260 | 8.8
R379 | PPA | 6675002932930 |  | Clinometers |  | 424.51 |  | 20.06 | 36.51 | 55.39 | 47.23 | 53.06 | 51.9 | 50.63 | 53.06 | 36.51 | 20.16
R380 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 184 |  |  | 26.59 | 31.65 | 53.17 | 35.79 | 30.64 | 6.16
R397 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 456 | 20.29 | 37.96 | 65.78 | 55.75 | 59.51 | 50.73 | 58.25 | 53.24 | 37.96 | 16.53
R3A7 | PPA | 4920001616963 |  | Boresight Equipment |  | 188.95 | 48.36 |  | 43.72 | 48.36 | 45.27 | 3.24
R479 | PPA | 6675002932930 |  | Clinometers |  | 500 |  | 24.5 | 42.5 | 42.5 | 39.5 | 42.5 | 41 | 42.5 | 41 | 42.5 | 42.5 | 41 | 42.5 | 15.5
R480 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 100 |  | 4.9 | 8.5 | 8.5 | 7.9 | 8.5 | 8.2 | 8.5 | 8.2 | 8.5 | 8.5 | 8.2 | 8.5 | 3.1
R497 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 185 |  | 9.07 | 15.73 | 15.73 | 14.62 | 15.73 | 15.17 | 15.73 | 15.17 | 15.73 | 15.73 | 15.17 | 15.73 | 5.69
V413 | PPA | 6625014962745 |  | Multiproduct Calibrator |  | 18 |  | 0.88 | 1.53 | 1.53 | 1.42 | 1.53 | 1.48 | 1.53 | 1.48 | 1.53 | 1.53 | 1.48 | 1.53 | 0.55
W375 | PPA | 8120015271059 |  | Cylinder, Compressed Gas |  | 5.2 |  | 1.08 | 2.08 | 2.04

## Actual Induction
Master Work Schedule Log (UNCLASSIFIED)
(Mon Mar 18 09:02:23 EDT 2024)
for Workload Year 2024
for SAC 2
for Status 3
MWSLIN | SOR | NSN | TAMCN | NOMENCLATURE | Prior | Current | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
[5 empty] | 502 | 166 | 27 | 43 | 13 | 34 | 22 | 27 | 0 | 0 | 0 | 0 | 0 | 0
C768 | PPA | 1240015541735 | E0846 | Thermal Elbow Assembly TSS | 84 | 0 |  |  |  | 0
D009 | PPB | 5895015525616 | A0123 | Console, Communications | 8 | 15 | 12 | 3
D046 | PPA | 5820200058054 | A0153 | Receiver-Transmitter, Radio | 192 | 0
D052 | PPA | 5998011423769 | A2179 | Electronic Component | 12 | 0
D081 | PPA | 6625014778172 | A7420 | Generator, Function, Electronic :33250A | 6 | 0
D084 | PPA | 6625015623698 | A7420 | Calibrator, Range Indicator | 11 | 0
D090 | PPA | 6625016533190 | A7523 | Calibrator, Frequency | 2 | 0
D091 | PPB | 6130015447811 | A2179 | Power Supply, ComTech |  | 2 | 2
D092 | PPA | 6625015658920 | A7420 | Oscilloscope | 1 | 0
D095 | PPA | 5998011418146 | A2179 | Circuit Card Assembly | 1 | 0
D097 | PPA | 5996015848748 | A0331 | Amplifier, Radio | 20 | 20 | 0 | 20
D098 | PPA | 5996016616649 | A0242 | Amplifier, Radio Frequency | 6 | 0 |  |  |  |  | 0
D0A2 | PPA | 6625014217497 | A7596 | Plug-In Unit, Electr | 1 | 0
D0A3 | PPA | 6625014925646 | A7596 | Plug-In Unit, Electrical-Electronic |  | 1 |  | 1
D752 | PPA | 6660015066613 | E1035 | Theodolite, Meteorological | 3 | 1 | 1 | 0
D755 | PPA | 1290015100540 | E0180 | Transit, Aming Circle | 35 | 20 | 0 | 10 | 5 | 5
D755 | PPB | 1290015100540 | E0180 | Transit, Aming Circle | 25 | 19 | 6 | 6 | 7
D769 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly | 4 | 1 | 1
D776 | PPA | 1440014583366 | E0942 | Armament, Control | 2 | 0
D785 | PPA | 4910015991753 | E7903 | Test Adapter Vehicle | 2 | 1 |  | 0 |  | 1
D798 | PPA | 2815015502615 | E0947 | Engine, Diesel | 9 | 0
D798 | PPB | 2815015502615 | E0947 | Engine, Diesel | 7 | 0
D7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section | 5 | 3 | 3
D815 | PPA | 5980016296933 | B1583 | Control-Display, Opt
D826 | PPB | 2815015891633 | B0071 | Engine, Diesel | 1 | 0
D842 | PPA | 4520016313780 | B0055 | Heater, Water, Liquid | 1 | 0
D930 | PPB | 1240015158265 | E0671 | Mount, Telescope | 13 | 0
E032 | PPB | 5820015709746 | A0097 | Vehicular, Adaptor Unit |  | 39 |  |  |  | 14 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0
E097 | PPA | 5996015848748 | A0331 | Amplifier, Radio |  | 30 |  |  |  | 10 | 20 | 0 | 0 | 0
E0A4 | PPA | 6625014925557 | A7596 | Plug-In Unit, Electronic Test Equip |  | 3 |  |  | 0 | 3
E0A5 | PPA | 5996016429980 | A0352 | Amplifier, Radio frequency |  | 1 |  |  |  | 1
E0A6 | PPA | 6625014925302 | A7596 | Plug-In Unit, Electric |  | 0 | [7 empty] | 0 |  |  | 0
E70S | PPA | 2815015502608 | E0947 | Engine, Diesel |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
E766 | PPB | 1025992979085 | E0671 | Buffer, Assembly, Special |  | 0 | [8 empty] | 0 | 0 | 0 | 0
E771 | PPB | 3040994887463 | E0671 | Accumulator, Hydraulic |  | 0 |  |  |  |  | 0 | 0
E772 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 0 | [5 empty] | 0 | 0 | 0 | 0
E776 | PPA | 1440014583366 | E0942 | Armament, Control |  | 0 | [7 empty] | 0
E7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 2 | [5 empty] | 2 | 0
E930 | PPB | 1240015158265 | E0671 | Mount, Telescope |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
L461 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
L463 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 0 | [5 empty] | 0 | 0 | 0
L464 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 0 | [5 empty] | 0 | 0
L465 | PPB | 5895016647511 | E0671 | Enclosure Assembly, Radio |  | 0 | [5 empty] | 0
M80C | DMISA | 2805015556505 | C4548 | Engine, Outboard Multi Fuel | 50 | 0
R2AA | DMISA | 5985015821343 | A0169 | Antenna |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0
R379 | PPA | 6675002932930 |  | Clinometers |  | 4 | 2 | 2 |  | 0 |  | 0 |  | 0
R380 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 2 |  |  | 1 |  | 1
R397 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 1 | 0 | 1 | 0 |  | 0 |  | 0
R3A7 | PPA | 4920001616963 |  | Boresight Equipment | 1 | 1 |  |  | 0 |  | 1
R479 | PPA | 6675002932930 |  | Clinometers |  | 0 |  | 0
R480 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 0 |  | 0
R497 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 0 |  | 0
V413 | PPA | 6625014962745 |  | Multiproduct Calibrator |  | 0 |  | 0
W375 | PPA | 8120015271059 |  | Cylinder, Compressed Gas |  | 0 |  | 0

## Actual Production
Master Work Schedule Log (UNCLASSIFIED)
(Mon Mar 18 09:02:23 EDT 2024)
for Workload Year 2024
for SAC 2
for Status 3
MWSLIN | SOR | NSN | TAMCN | NOMENCLATURE | Prior | Current | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
[5 empty] | 373 | 166 | 62 | 18 | 21 | 23 | 25 | 17 | 0 | 0 | 0 | 0 | 0 | 0
C768 | PPA | 1240015541735 | E0846 | Thermal Elbow Assembly TSS | 84 | 0 | [5 empty] | 0
D009 | PPB | 5895015525616 | A0123 | Console, Communications |  | 23 | 11 | 5 | 4 | 3
D046 | PPA | 5820200058054 | A0153 | Receiver-Transmitter, Radio | 166 | 26 | 21 | 5 | 0
D052 | PPA | 5998011423769 | A2179 | Electronic Component | 8 | 4 | 4
D081 | PPA | 6625014778172 | A7420 | Generator, Function, Electronic :33250A | 3 | 3 | 3
D084 | PPA | 6625015623698 | A7420 | Calibrator, Range Indicator | 7 | 4 | 4 | 0
D090 | PPA | 6625016533190 | A7523 | Calibrator, Frequency | 1 | 1 | 1 |  | 0
D091 | PPB | 6130015447811 | A2179 | Power Supply, ComTech |  | 1 |  | 0 |  | 1
D092 | PPA | 6625015658920 | A7420 | Oscilloscope |  | 1 |  | 0 | 1
D095 | PPA | 5998011418146 | A2179 | Circuit Card Assembly | 1 | 0
D097 | PPA | 5996015848748 | A0331 | Amplifier, Radio |  | 19 |  |  |  |  | 2 | 17 | 0 | 0 | 0
D098 | PPA | 5996016616649 | A0242 | Amplifier, Radio Frequency |  | 0 | [6 empty] | 0 | 0 | 0
D0A2 | PPA | 6625014217497 | A7596 | Plug-In Unit, Electr |  | 1 | 1 | 0
D0A3 | PPA | 6625014925646 | A7596 | Plug-In Unit, Electrical-Electronic |  | 1 |  | 1
D752 | PPA | 6660015066613 | E1035 | Theodolite, Meteorological | 1 | 3 | 2 | 1 | 0 |  | 0
D755 | PPA | 1290015100540 | E0180 | Transit, Aming Circle | 15 | 19 | 8 | 0 | 5 | 6 | 0 | 0
D755 | PPB | 1290015100540 | E0180 | Transit, Aming Circle | 17 | 18 | 1 | 4 | 3 | 6 | 4
D769 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly |  | 5 | 0 |  |  | 0 | 5
D776 | PPA | 1440014583366 | E0942 | Armament, Control |  | 0 | 0
D785 | PPA | 4910015991753 | E7903 | Test Adapter Vehicle |  | 3 | 2 |  |  |  | 1
D798 | PPA | 2815015502615 | E0947 | Engine, Diesel |  | 6 |  | 0 | 2 | 3 | 1
D798 | PPB | 2815015502615 | E0947 | Engine, Diesel | 6 | 1 | 1
D7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section | 5 | 3 |  |  | 3
D815 | PPA | 5980016296933 | B1583 | Control-Display, Opt
D826 | PPB | 2815015891633 | B0071 | Engine, Diesel |  | 1 | 0 |  |  |  | 1
D842 | PPA | 4520016313780 | B0055 | Heater, Water, Liquid |  | 0 |  | 0
D930 | PPB | 1240015158265 | E0671 | Mount, Telescope | 9 | 4 | 3 | 1
E032 | PPB | 5820015709746 | A0097 | Vehicular, Adaptor Unit |  | 11 |  |  |  |  | 11 | 0 |  | 0 | 0 | 0 | 0 | 0
E097 | PPA | 5996015848748 | A0331 | Amplifier, Radio |  | 0 | [9 empty] | 0 | 0 | 0
E0A4 | PPA | 6625014925557 | A7596 | Plug-In Unit, Electronic Test Equip |  | 3 |  |  |  | 3 | 0
E0A5 | PPA | 5996016429980 | A0352 | Amplifier, Radio frequency |  | 0 | [5 empty] | 0
E0A6 | PPA | 6625014925302 | A7596 | Plug-In Unit, Electric |  | 0 | [9 empty] | 0
E70S | PPA | 2815015502608 | E0947 | Engine, Diesel |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
E766 | PPB | 1025992979085 | E0671 | Buffer, Assembly, Special |  | 0 | [10 empty] | 0 | 0
E771 | PPB | 3040994887463 | E0671 | Accumulator, Hydraulic |  | 0 | [6 empty] | 0 | 0
E772 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 0 | [7 empty] | 0 | 0 | 0 | 0
E776 | PPA | 1440014583366 | E0942 | Armament, Control |  | 0 | [10 empty] | 0
E7D5 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 0 | [7 empty] | 0 | 0
E930 | PPB | 1240015158265 | E0671 | Mount, Telescope |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0
L461 | PPB | 1220016473873 | E0671 | Digital Fire Control System Assembly |  | 0 | [8 empty] | 0 | 0 | 0 | 0
L463 | PPB | 5998998407932 | E0671 | ELEC, COMPONENT |  | 0 | [7 empty] | 0 | 0 | 0
L464 | PPB | 7025016473875 | E0671 | Display Unit, Chief of Section |  | 0 | [7 empty] | 0 | 0
L465 | PPB | 5895016647511 | E0671 | Enclosure Assembly, Radio |  | 0 | [8 empty] | 0
M80C | DMISA | 2805015556505 | C4548 | Engine, Outboard Multi Fuel | 50 | 0
R2AA | DMISA | 5985015821343 | A0169 | Antenna |  | 0 | [7 empty] | 0 |  | 0 | 0
R379 | PPA | 6675002932930 |  | Clinometers |  | 2 |  |  | 2 |  | 0 |  | 0 |  | 0 |  | 0
R380 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 1 |  |  |  | 1 |  | 0 |  | 0
R397 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 1 |  |  | 1 | 0 |  | 0 |  | 0 |  | 0
R3A7 | PPA | 4920001616963 |  | Boresight Equipment |  | 1 | 0 | 1 |  |  |  | 0
R479 | PPA | 6675002932930 |  | Clinometers |  | 0
R480 | PPA | 4933001441857 |  | Fixture, Checking, Guide Bar Housing |  | 0
R497 | PPA | 4920011063361 |  | Fixture, Aircraft Maintenance |  | 0
V413 | PPA | 6625014962745 |  | Multiproduct Calibrator |  | 0
W375 | PPA | 8120015271059 |  | Cylinder, Compressed Gas |  | 0 |  |  |  | 0